## Submittal Log
Submittal Log — Cedar Lake
Submittal # | Spec Section | Spec Title | Type | Description | Manufacturer | Product | Status | Responsible Party | Due Date | Submitted Date | Approved Date | Rev | Notes
CL-0001-001 | 01 10 00 | SUMMARY OF THE WORK | other | CONTRACTOR’S LIST OF SUBCONTRACTORS-SUPPLIERS information |  |  | draft |  |  |  |  | 0
CL-0001-002 | 01 10 00 | SUMMARY OF THE WORK | other | Submittal Coordinator Qualifications, including resume and references, and other certification, licenses, or other requested information |  |  | draft |  |  |  |  | 0
CL-0001-003 | 01 10 00 | SUMMARY OF THE WORK | schedule | Preliminary Project Schedule related information |  |  | draft |  |  |  |  | 0
CL-0001-004 | 01 11 00 | SAFETY | other | Emergency Action and Evacuation Plan, including fire protection and emergency response |  |  | draft |  |  |  |  | 0
CL-0001-005 | 01 33 00 | SUBMITTALS | other | Submittal Coordinator Qualifications, including resume, references, and other certification, licenses, or requested information |  |  | draft |  |  |  |  | 0
CL-0001-006 | 01 74 19 | CONSTRUCTION WASTE MANAGEMENT | closeout | Final Waste Management Report, compiling all monthly data for the duration of the project; include explanation of actual waste managed, lessons learned, and a final CWM Reporting Form |  |  | draft |  |  |  |  | 0
CL-0001-007 | 01 74 19 | CONSTRUCTION WASTE MANAGEMENT | other | Calculations and supporting documentation to demonstrate disposal, recycling, and/or salvage rates meeting the requirements of the CWM Plan |  |  | draft |  |  |  |  | 0
CL-0001-008 | 01 74 19 | CONSTRUCTION WASTE MANAGEMENT | other | Construction Waste Management (CWM) Plan |  |  | draft |  |  |  |  | 0
CL-0001-009 | 01 77 16 | CONTRACT CLOSEOUT | closeout | Directory, listing names, addresses, and telephone numbers of Architect/Engineer, Contractor, subcontractors, and major equipment suppliers |  |  | draft |  |  |  |  | 0
CL-0001-010 | 02 33 13 | UNDERGROUND UTILITY LOCATOR SERVICE | certificates | names of persons that will be performing the Work, including the number of years of experience and training; copy of training certificates for locator equipment proving the person performing the locator service are trained on the equipment being used |  |  | draft |  |  |  |  | 0
CL-0001-011 | 02 33 13 | UNDERGROUND UTILITY LOCATOR SERVICE | other | all documentation referenced to existing data (horizontal and vertical) previously established |  |  | draft |  |  |  |  | 0
CL-0001-012 | 02 33 13 | UNDERGROUND UTILITY LOCATOR SERVICE | other | description of types of utility locator equipment that company will utilize to perform the underground utility investigation |  |  | draft |  |  |  |  | 0
CL-0001-013 | 02 33 13 | UNDERGROUND UTILITY LOCATOR SERVICE | other | detailed experience and qualification information about the underground utility locator service company and the persons that will be performing the Work |  |  | draft |  |  |  |  | 0
CL-0001-014 | 02 33 13 | UNDERGROUND UTILITY LOCATOR SERVICE | other | detailed written report and scaled drawings of the subsurface investigation, documenting all underground utilities and service connections located and identified |  |  | draft |  |  |  |  | 0
CL-0001-015 | 03 10 00 | CONCRETE FORMING AND ACCESSORIES | other | Field quality-control reports |  |  | draft |  |  |  |  | 0
CL-0001-016 | 03 10 00 | CONCRETE FORMING AND ACCESSORIES | other | Qualification data for testing and inspection agency |  |  | draft |  |  |  |  | 0
CL-0001-017 | 03 10 00 | CONCRETE FORMING AND ACCESSORIES | other | Research reports for insulating concrete forms indicating compliance with International Code Council Acceptance Criteria AC353 |  |  | draft |  |  |  |  | 0
CL-0001-018 | 03 10 00 | CONCRETE FORMING AND ACCESSORIES | product_data | Product data for exposed surface form-facing material, concealed surface form-facing material, forms for cylindrical columns, pan-type forms, void forms, form liners, insulating concrete forms, form ties, waterstops, and form-release agent | CETCO, Minerals Technologies Inc., Sika Corporation, Williams Products, Inc., JP Specialties, Inc., BoMetals, Inc., Vinylex Waterstop & Accessories, Carlisle Coatings & Waterproofing Inc., Henry Company, Adeka Corporation, Kryton International Inc. | Flexible Rubber Waterstops, Flexible Rubber Waterstops, Flexible Rubber Waterstops, Flexible Rubber Waterstops, Chemically Resistant Flexible Waterstops, Flexible PVC Waterstops, Flexible PVC Waterstops, Self-Expanding Butyl Strip Waterstops, Self-Expanding Butyl Strip Waterstops, Self-Expanding Rubber Strip Waterstops, Self-Expanding Rubber Strip Waterstops | draft |  |  |  |  | 0
CL-0001-019 | 03 10 00 | CONCRETE FORMING AND ACCESSORIES | samples | Samples for waterstops and form liners; 12-inch by 12-inch sample indicating texture for form liners |  |  | draft |  |  |  |  | 0
CL-0001-020 | 03 10 00 | CONCRETE FORMING AND ACCESSORIES | shop_drawings | Shop drawings prepared and signed and sealed by a qualified professional engineer, registered in New York State, detailing fabrication, assembly, and support of forms; include dimensions and form tie locations for exposed vertical concrete walls; dimensions and locations of construction and movement joints; location of waterstops; form liner layout and form line termination details; proposed schedule and sequence of stripping of forms, shoring removal, and reshoring installation and removal; layout of insulating concrete forms, dimensions, course heights, form types, and details |  |  | draft |  |  |  |  | 0
CL-0001-021 | 03 20 00 | CONCRETE REINFORCING | certificates | Material certificates for epoxy-coated reinforcement, dual-coated reinforcement, and documentation to confirm compliance with General Conditions Article 25.4 Domestic Steel. |  |  | draft |  |  |  |  | 0
CL-0001-022 | 03 20 00 | CONCRETE REINFORCING | certificates | Welding certificates, including welding procedure specification for reinforcement to be welded in accordance with AWS D1.4. |  |  | draft |  |  |  |  | 0
CL-0001-023 | 03 20 00 | CONCRETE REINFORCING | other | Field quality-control reports. |  |  | draft |  |  |  |  | 0
CL-0001-024 | 03 20 00 | CONCRETE REINFORCING | other | Qualification statements for testing and inspection agency. |  |  | draft |  |  |  |  | 0
CL-0001-025 | 03 20 00 | CONCRETE REINFORCING | product_data | Product data for each type of steel reinforcement, epoxy repair coating, zinc repair material, bar supports, mechanical splice couplers, and structural thermal break insulated connection system. |  |  | draft |  |  |  |  | 0
CL-0001-026 | 03 20 00 | CONCRETE REINFORCING | shop_drawings | Construction joint layout indicating proposed construction joints required to build the structure. |  |  | draft |  |  |  |  | 0
CL-0001-027 | 03 20 00 | CONCRETE REINFORCING | shop_drawings | Shop drawings including placing drawings that detail fabrication, bending, and placement; bar sizes, lengths, materials, grades, bar schedules, stirrup spacing, bent bar diagrams, bar arrangement, location of splices, lengths of lap splices, details of mechanical splice couplers, details of welding splices, tie spacing, hoop spacing, and supports for concrete reinforcement; and for structural thermal break insulated connection system, general configuration, insulation dimensions, tension bars, compression pads, shear bars, and dimensions. |  |  | draft |  |  |  |  | 0
CL-0001-028 | 03 20 00 | CONCRETE REINFORCING | test_reports | Material test reports for steel reinforcement, including mill test analysis for reinforcement to be welded, and for mechanical splice couplers. |  |  | draft |  |  |  |  | 0
CL-0001-029 | 03 30 00 | CAST-IN-PLACE CONCRETE | certificates | Material Certificates for cementitious materials, admixtures, fiber reinforcement, curing compounds, floor and slab treatments, bonding agents, adhesives, vapor retarders, semirigid joint filler, joint-filler strips, and repair materials, signed by manufacturers. |  |  | draft |  |  |  |  | 0
CL-0001-030 | 03 30 00 | CAST-IN-PLACE CONCRETE | other | Field quality-control reports. |  |  | draft |  |  |  |  | 0
CL-0001-031 | 03 30 00 | CAST-IN-PLACE CONCRETE | other | Floor surface flatness and levelness measurements report indicating compliance with specified tolerances. |  |  | draft |  |  |  |  | 0
CL-0001-032 | 03 30 00 | CAST-IN-PLACE CONCRETE | other | Qualification Data for installer, ready-mixed concrete manufacturer, and testing agency. |  |  | draft |  |  |  |  | 0
CL-0001-033 | 03 30 00 | CAST-IN-PLACE CONCRETE | other | Research Reports for concrete admixtures in accordance with UNIFORM CODE Acceptance Criteria AC198 and for sheet vapor retarder/termite barrier showing compliance with UNIFORM CODE AC380. |  |  | draft |  |  |  |  | 0
CL-0001-034 | 03 30 00 | CAST-IN-PLACE CONCRETE | product_data | Product data for Portland cement, fly ash, slag cement, blended hydraulic cement, silica fume, performance-based hydraulic cement, aggregates, admixtures, fiber reinforcement, vapor retarders, floor and slab treatments, curing materials, joint fillers, and repair materials. | BASF Corporation, Euclid Chemical Company (The); an RPM company, GCP Applied Technologies Inc., Sika Corporation, Aggregate Industries (US); Lafarge, Barrier-Bac; Inteplast Group, AQUAFIN, Inc., Kryton International Inc., Xypex Chemical Corporation, ABC Polymer Industries, LLC., Propex Operating Company, LLC., ISI Building Products, Raven Industries, Inc., Reef Industries, Inc., Stego Industries, LLC., Tex-Trude, Polyguard Products, Inc., McTech Group, Inc. | Admixtures, Admixtures, Admixtures, Admixtures, Admixtures, Vapor Retarders, Admixtures, Admixtures, Admixtures, Fiber Reinforcement, Fiber Reinforcement, Vapor Retarders, Vapor Retarders, Vapor Retarders, Vapor Retarders, Vapor Retarders, Floor Slab Protective Covering | draft |  |  |  |  | 0
CL-0001-035 | 03 30 00 | CAST-IN-PLACE CONCRETE | samples | Samples for vapor retarder. | Barrier-Bac; Inteplast Group, ISI Building Products, Raven Industries, Inc., Reef Industries, Inc., Stego Industries, LLC., Tex-Trude, Polyguard Products, Inc. | Vapor Retarders, Vapor Retarders, Vapor Retarders, Vapor Retarders, Vapor Retarders, Vapor Retarders, Vapor Retarder/Termite Barrier | draft |  |  |  |  | 0
CL-0001-036 | 03 30 00 | CAST-IN-PLACE CONCRETE | schedule | Concrete Schedule for each location of each Class of concrete indicated in Concrete Mixtures Article, including concrete class designation, location within project, exposure class designation, formed surface finish designation and final finish, curing process, and floor treatment if any. |  |  | draft |  |  |  |  | 0
CL-0001-037 | 03 30 00 | CAST-IN-PLACE CONCRETE | shop_drawings | Construction Joint Layout indicating proposed construction joints required to construct the structure. |  |  | draft |  |  |  |  | 0
CL-0001-038 | 03 30 00 | CAST-IN-PLACE CONCRETE | test_reports | Material Test Reports for Portland cement, fly ash, slag cement, blended hydraulic cement, silica fume, performance-based hydraulic cement, aggregates, and admixtures, including independent test reports for permeability-reducing admixture. |  |  | draft |  |  |  |  | 0
CL-0001-039 | 03 30 00 | CAST-IN-PLACE CONCRETE | test_reports | Preconstruction Test Reports for each mix design. |  |  | draft |  |  |  |  | 0
CL-0001-040 | 05 12 00 | STRUCTURAL STEEL FRAMING | certificates | Paint compatibility certificates from manufacturers of topcoats applied over shop primers certifying compatibility with shop primers |  |  | draft |  |  |  |  | 0
CL-0001-041 | 05 12 00 | STRUCTURAL STEEL FRAMING | certificates | Welding certificates |  |  | draft |  |  |  |  | 0
CL-0001-042 | 05 12 00 | STRUCTURAL STEEL FRAMING | design_data | Delegated-design submittal for structural-steel connections, including analysis data signed and sealed by the qualified professional engineer in New York State responsible for preparation |  |  | draft |  |  |  |  | 0
CL-0001-043 | 05 12 00 | STRUCTURAL STEEL FRAMING | design_data | Welding Procedure Specifications (WPSs) and Procedure Qualification Records (PQRs) for each welded joint, including power source and electrode manufacturer and trade name for demand-critical welds |  |  | draft |  |  |  |  | 0
CL-0001-044 | 05 12 00 | STRUCTURAL STEEL FRAMING | other | Field quality-control reports |  |  | draft |  |  |  |  | 0
CL-0001-045 | 05 12 00 | STRUCTURAL STEEL FRAMING | other | Qualification data for installer fabricator, professional engineer, and testing agency |  |  | draft |  |  |  |  | 0
CL-0001-046 | 05 12 00 | STRUCTURAL STEEL FRAMING | other | Source quality-control reports, including documentation to confirm compliance with General Conditions Article 25.4 Domestic Steel |  |  | draft |  |  |  |  | 0
CL-0001-047 | 05 12 00 | STRUCTURAL STEEL FRAMING | product_data | Product data for structural-steel materials; high-strength, bolt-nut-washer assemblies; shear stud connectors; anchor rods; threaded rods; forged-steel hardware; slide bearings; prefabricated building columns; shop primer; galvanized-steel primer; etching cleaner; galvanized repair paint; shrinkage-resistant grout |  |  | draft |  |  |  |  | 0
CL-0001-048 | 05 12 00 | STRUCTURAL STEEL FRAMING | shop_drawings | Shop drawings showing fabrication of structural-steel components, including details of cuts, connections, splices, camber, holes, erection drawings, embedment and base plate drawings, weld symbols, bolt information, seismic-load-resisting system members and connections, protected zones, demand-critical welds, and members not to be shop primed |  |  | draft |  |  |  |  | 0
CL-0001-049 | 05 12 00 | STRUCTURAL STEEL FRAMING | test_reports | Mill test reports for structural-steel materials, including chemical and physical properties |  |  | draft |  |  |  |  | 0
CL-0001-050 | 05 12 00 | STRUCTURAL STEEL FRAMING | test_reports | Product test reports for bolts, nuts, and washers, direct-tension indicators, tension-control high-strength bolt-nut-washer assemblies, and shear stud connectors |  |  | draft |  |  |  |  | 0
CL-0001-051 | 05 31 00 | STEEL DECKING | certificates | Product certificates for each type of steel deck |  |  | draft |  |  |  |  | 0
CL-0001-052 | 05 31 00 | STEEL DECKING | certificates | Welding certificates |  |  | draft |  |  |  |  | 0
CL-0001-053 | 05 31 00 | STEEL DECKING | other | Field quality-control reports |  |  | draft |  |  |  |  | 0
CL-0001-054 | 05 31 00 | STEEL DECKING | other | Research reports for steel deck from ICC-ES |  |  | draft |  |  |  |  | 0
CL-0001-055 | 05 31 00 | STEEL DECKING | other | Source quality-control reports |  |  | draft |  |  |  |  | 0
CL-0001-056 | 05 31 00 | STEEL DECKING | product_data | Product data for roof deck and composite floor deck | Canam Steel Corporation, Canam Group, Inc., Epic Metals Corporation, New Millennium Building Systems, LLC., Nucor Corporation | Roof Deck, Composite Floor Deck | draft |  |  |  |  | 0
CL-0001-057 | 05 31 00 | STEEL DECKING | shop_drawings | Shop drawings showing layout and types of deck panels, anchorage details, reinforcing channels, pans, cut deck openings, special jointing, accessories, and attachments to other construction |  |  | draft |  |  |  |  | 0
CL-0001-058 | 05 31 00 | STEEL DECKING | test_reports | Product test reports for power-actuated mechanical fasteners, screw fasteners, and acoustical roof deck |  |  | draft |  |  |  |  | 0
CL-0001-059 | 05 50 00 | METAL FABRICATIONS | certificates | Mill certificates signed by stainless steel manufacturers, certifying products furnished comply with requirements |  |  | draft |  |  |  |  | 0
CL-0001-060 | 05 50 00 | METAL FABRICATIONS | certificates | Paint compatibility certificates from manufacturers of topcoats applied over shop primers, certifying shop primers are compatible with topcoats |  |  | draft |  |  |  |  | 0
CL-0001-061 | 05 50 00 | METAL FABRICATIONS | certificates | Welding certificates |  |  | draft |  |  |  |  | 0
CL-0001-062 | 05 50 00 | METAL FABRICATIONS | closeout | Documentation to confirm compliance with General Conditions Article 25.4 Domestic Steel |  |  | draft |  |  |  |  | 0
CL-0001-063 | 05 50 00 | METAL FABRICATIONS | design_data | Delegated-design submittal for ladders, including analysis and design data signed and sealed by the qualified professional engineer in New York State responsible for preparation |  |  | draft |  |  |  |  | 0
CL-0001-064 | 05 50 00 | METAL FABRICATIONS | other | Qualification data for professional engineer's experience with delegated-design engineering services, including documentation that engineer is licensed and registered in New York State |  |  | draft |  |  |  |  | 0
CL-0001-065 | 05 50 00 | METAL FABRICATIONS | product_data | Product Data for nonslip aggregates and nonslip-aggregate surface finishes; fasteners; shop primers; shrinkage-resisting grout; prefabricated building columns; slotted channel framing; manufactured metal ladders; ladder safety cages; alternating tread devices; metal ships' ladders; metal bollards; pipe downspoutguards; abrasive metal nosings, treads, and thresholds; cast-iron wheel guards; metal downspout boots | Harsco Industrial IKG, a Division of Harsco Corporation, W.S. Molnar Company | Abrasive-Surface Floor Plate | draft |  |  |  |  | 0
CL-0001-066 | 05 50 00 | METAL FABRICATIONS | samples | Samples for verification for each type and finish of extruded nosing and tread |  |  | draft |  |  |  |  | 0
CL-0001-067 | 05 50 00 | METAL FABRICATIONS | shop_drawings | Shop Drawings showing fabrication and installation details, including plans, elevations, sections, details of metal fabrications and their connections, anchorage, and accessory items for listed metal fabrications |  |  | draft |  |  |  |  | 0
CL-0001-068 | 05 50 00 | METAL FABRICATIONS | test_reports | Research reports for post-installed anchors |  |  | draft |  |  |  |  | 0
CL-0001-069 | 05 50 00 | METAL FABRICATIONS | test_reports | Source quality-control reports |  |  | draft |  |  |  |  | 0
CL-0001-070 | 06 10 00 | ROUGH CARPENTRY | certificates | Material certificates for dimension lumber specified to comply with minimum allowable unit stresses, indicating species, grade selected for each use, and design values approved by the ALSC Board of Review. |  |  | draft |  |  |  |  | 0
CL-0001-071 | 06 10 00 | ROUGH CARPENTRY | other | Evaluation reports for metal framing anchors, from ICC-ES. | Cleveland Steel Specialty Co., Phoenix Metal Products, Inc., Simpson Strong-Tie Co., Inc. | Metal framing anchors | draft |  |  |  |  | 0
CL-0001-072 | 06 10 00 | ROUGH CARPENTRY | product_data | Fastener pattern templates for exposed framing. |  |  | draft |  |  |  |  | 0
CL-0001-073 | 06 10 00 | ROUGH CARPENTRY | product_data | Product data for each type of process and factory-fabricated product, including component materials, dimensions, construction and application details. Include data for wood-preservative treatment, fire-retardant treatment, and products receiving waterborne treatment. |  |  | draft |  |  |  |  | 0
CL-0001-074 | 06 41 16 | PLASTIC-LAMINATE-CLAD ARCHITECTURAL CABINETS | certificates | Product certificates for composite wood products, thermoset decorative panels, high-pressure decorative laminate, glass, and adhesives. |  |  | draft |  |  |  |  | 0
CL-0001-075 | 06 41 16 | PLASTIC-LAMINATE-CLAD ARCHITECTURAL CABINETS | certificates | Qualification data for manufacturer and installer. |  |  | draft |  |  |  |  | 0
CL-0001-076 | 06 41 16 | PLASTIC-LAMINATE-CLAD ARCHITECTURAL CABINETS | closeout | Quality Standard Compliance Certificates: AWI Quality Certification Program certificates. | Architectural Woodwork Institute (AWI) | Quality Standard Compliance Certificates | draft |  |  |  |  | 0
CL-0001-077 | 06 41 16 | PLASTIC-LAMINATE-CLAD ARCHITECTURAL CABINETS | other | Field quality-control reports. |  |  | draft |  |  |  |  | 0
CL-0001-078 | 06 41 16 | PLASTIC-LAMINATE-CLAD ARCHITECTURAL CABINETS | product_data | Product data for each type of product, including manufacturer’s installation instructions; fire-retardant treatment data from chemical-treatment manufacturer and certification by treating plant that treated materials comply with requirements. |  |  | draft |  |  |  |  | 0
CL-0001-079 | 06 41 16 | PLASTIC-LAMINATE-CLAD ARCHITECTURAL CABINETS | samples | Samples for each exposed product and for each color and texture specified, in manufacturer's or manufacturer's standard size. |  |  | draft |  |  |  |  | 0
CL-0001-080 | 06 41 16 | PLASTIC-LAMINATE-CLAD ARCHITECTURAL CABINETS | samples | Samples for initial selection for each type of exposed finish. |  |  | draft |  |  |  |  | 0
CL-0001-081 | 06 41 16 | PLASTIC-LAMINATE-CLAD ARCHITECTURAL CABINETS | samples | Samples for verification: plastic laminates, thermoset decorative panels, corner pieces, and exposed cabinet hardware and accessories. |  |  | draft |  |  |  |  | 0
CL-0001-082 | 06 41 16 | PLASTIC-LAMINATE-CLAD ARCHITECTURAL CABINETS | shop_drawings | Shop drawings showing plans, elevations, sections, attachment details, large-scale details, furring, blocking, hanging strips, concealed blocking and reinforcement, and cutouts and holes for items installed in plastic-laminate architectural cabinets. |  |  | draft |  |  |  |  | 0
CL-0001-083 | 06 41 16 | PLASTIC-LAMINATE-CLAD ARCHITECTURAL CABINETS | test_reports | Evaluation reports for fire-retardant-treated materials from ICC-ES. |  |  | draft |  |  |  |  | 0
CL-0001-084 | 07 11 13 | BITUMINOUS DAMPPROOFING | product_data | Manufacturer’s installation instructions and product data | BASF Corporation, Henry Company, Karnak Corporation, W.R. Meadows, Inc. | Cold-applied, emulsified-asphalt dampproofing | draft |  |  |  |  | 0
CL-0001-085 | 07 11 13 | BITUMINOUS DAMPPROOFING | product_data | Product data for each type of product | BASF Corporation, Henry Company, Karnak Corporation, W.R. Meadows, Inc. | Cold-applied, emulsified-asphalt dampproofing | draft |  |  |  |  | 0
CL-0001-086 | 07 26 00 | VAPOR RETARDERS | product_data | Product Data: For each type of product. | Henry Company, Raven Industries, Inc., Stego Industries, LLC., W. R. Meadows, Inc. | Moistop Ultra 10, VaporBlock 10 (VB10), Stego Wrap 10-Mil Class A Vapor Retarder, Perminator 10 Mil Underslab Vapor Barrier, Moistop Ultra 15, VaporBlock 15 (VB15), Stego Wrap 15-Mil Class A Vapor Retarder, Perminator 15 Mil Underslab Vapor Barrier | draft |  |  |  |  | 0
CL-0001-087 | 07 26 00 | VAPOR RETARDERS | samples | Samples: Vapor Retarder Material: 12 inches square. Pressure-Sensitive Tape: 36 inches long piece minimum. |  |  | draft |  |  |  |  | 0
CL-0001-088 | 07 26 00 | VAPOR RETARDERS | test_reports | Product Test Reports: For each product, for tests performed by a qualified testing agency. |  |  | draft |  |  |  |  | 0
CL-0001-089 | 07 72 53 | SNOW GUARDS | design_data | Delegated-design analysis reports signed and sealed by the qualified professional engineer responsible for their preparation, including calculation of number and location of snow guards. |  |  | draft |  |  |  |  | 0
CL-0001-090 | 07 72 53 | SNOW GUARDS | other | Qualification data for professional engineer experience with providing delegated design engineering services, including documentation that the Director’s Representative is licensed in the jurisdiction in which the Project is located. |  |  | draft |  |  |  |  | 0
CL-0001-091 | 07 72 53 | SNOW GUARDS | product_data | Product data for each type of product, including construction details, material descriptions, dimensions of individual components and profiles, and finishes. | Zaleski Snow-Guard and Roofing Specialties Inc. | Polycarbonate Flat-Mounted Snow Guards | draft |  |  |  |  | 0
CL-0001-092 | 07 72 53 | SNOW GUARDS | samples | Full-size unit sample with installation hardware for pad-type snow guards. |  |  | draft |  |  |  |  | 0
CL-0001-093 | 07 72 53 | SNOW GUARDS | shop_drawings | Roof plans showing layouts and attachment details of snow guards, including details of rail-type snow guards. |  |  | draft |  |  |  |  | 0
CL-0001-094 | 07 72 53 | SNOW GUARDS | test_reports | Product test reports for each type of snow guard, for tests performed by a qualified testing agency, indicating load at failure of attachment to roof system identical to roof system used on this Project. |  |  | draft |  |  |  |  | 0
CL-0001-095 | 07 92 00 | JOINT SEALANTS | certificates | Company Field Advisor Data: Name, Business Address and Telephone Number of Company Field Advisor |  |  | draft |  |  |  |  | 0
CL-0001-096 | 07 92 00 | JOINT SEALANTS | certificates | Installer’s Qualifications Data: Affidavit required under Quality Assurance Article |  |  | draft |  |  |  |  | 0
CL-0001-097 | 07 92 00 | JOINT SEALANTS | certificates | Qualification Data for qualified testing agency. |  |  | draft |  |  |  |  | 0
CL-0001-098 | 07 92 00 | JOINT SEALANTS | closeout | Sample Warranties for special warranties. |  |  | draft |  |  |  |  | 0
CL-0001-099 | 07 92 00 | JOINT SEALANTS | product_data | Product Data for each joint-sealant product, including manufacturer's installation instructions. | Dowsil, GE Construction Sealants, Pecora Corporation, Tremco Incorporated, Bostik, Master Builders Solutions, Sika Corporation, Henkel Adhesives | 790 Silicone Building Sealant, 756 SMS Building Sealant (cold weather application), 791, 795, Contractors Concrete Sealant (CCS), SCS2000 SilPruf Sealant, Contractors Weatherproofing Sealant (CWS), SWS Sealant, 300SL, NS Parking Structure Sealant, Parking Structure Sealant FC or SL, 736 Heat Resistant Sealant, Hi-Temp Sealant Red, Loctite SI 596, TremPro 644 HT, 890FTS, 890NST, 864NST, 895NST, Dymonic 100, Chem-Calk 915, MasterSeal NP1, Sikaflex-1a, Chem-Calk 916 Textured, Sikaflex Textured Sealant, Vulkem 116, Vulkem 45SSL, Sikaflex-1c SL, Dynatrol II, Joint Sealants; Sikaflex 2c NS EZ Mix, Vulkem 445SSL, Urexpan NR 200, THC 900/901, Sikaflex-2c SL, 786, Tub/Tile/Ceramic Sealant, SCS1700 Sanitary, Tub & Tile Caulk | draft |  |  |  |  | 0
CL-0001-100 | 07 92 00 | JOINT SEALANTS | samples | Samples for Initial Selection: Manufacturer's color charts consisting of strips of cured sealants showing the full range of colors available for each product exposed to view. |  |  | draft |  |  |  |  | 0
CL-0001-101 | 07 92 00 | JOINT SEALANTS | samples | Samples for Verification: For each kind and color of joint sealant required, provide samples with joint sealants in 1/2-inch-wide joints formed between two 6-inch-long strips of material matching adjacent exposed surfaces. |  |  | draft |  |  |  |  | 0
CL-0001-102 | 07 92 00 | JOINT SEALANTS | samples | Samples for joint fillers, gaskets, joint primer/sealer/conditioners, backer rods, bond breaker tape, and sealants. |  |  | draft |  |  |  |  | 0
CL-0001-103 | 07 92 00 | JOINT SEALANTS | schedule | Joint-Sealant Schedule including joint-sealant application, joint location, designation, manufacturer and product name, formulation, and color. |  |  | draft |  |  |  |  | 0
CL-0001-104 | 07 92 00 | JOINT SEALANTS | schedule | Preconstruction Laboratory Test Schedule for each joint sealant and substrate material to be tested, including joint-sealant location and designation, manufacturer and product name, substrate material, proposed test, and number of samples required. |  |  | draft |  |  |  |  | 0
CL-0001-105 | 07 92 00 | JOINT SEALANTS | test_reports | Field-Adhesion-Test Reports for each sealant application tested. |  |  | draft |  |  |  |  | 0
CL-0001-106 | 07 92 00 | JOINT SEALANTS | test_reports | Preconstruction Field-Adhesion-Test Reports indicating which sealants and joint preparation methods resulted in optimum adhesion to joint substrates. |  |  | draft |  |  |  |  | 0
CL-0001-107 | 07 92 00 | JOINT SEALANTS | test_reports | Preconstruction Laboratory Test Reports from sealant manufacturer indicating compatibility and adhesion testing of joint substrates and joint-sealant backings, and written recommendations for primers and substrate preparation. |  |  | draft |  |  |  |  | 0
CL-0001-108 | 07 92 00 | JOINT SEALANTS | test_reports | Product Test Reports for each kind of joint sealant, for tests performed by manufacturer and witnessed by a qualified testing agency. |  |  | draft |  |  |  |  | 0
CL-0001-109 | 08 11 13 | HOLLOW METAL DOORS AND FRAMES | closeout | Record documents for fire-rated doors, listing door numbers and applicable room name and number to which each door accesses |  |  | draft |  |  |  |  | 0
CL-0001-110 | 08 11 13 | HOLLOW METAL DOORS AND FRAMES | product_data | Product Data for each type of product |  |  | draft |  |  |  |  | 0
CL-0001-111 | 08 11 13 | HOLLOW METAL DOORS AND FRAMES | samples | Samples for initial selection for hollow-metal doors and frames with factory-applied color finishes |  |  | draft |  |  |  |  | 0
CL-0001-112 | 08 11 13 | HOLLOW METAL DOORS AND FRAMES | samples | Samples for verification: finishes for each type of exposed finish required, and fabrication samples for doors and frames |  |  | draft |  |  |  |  | 0
CL-0001-113 | 08 11 13 | HOLLOW METAL DOORS AND FRAMES | schedule | Product schedule for hollow-metal doors and frames, including egress door inspector documentation of compliance with NFPA 101, Section 7.2.1.15.4 |  |  | draft |  |  |  |  | 0
CL-0001-114 | 08 11 13 | HOLLOW METAL DOORS AND FRAMES | shop_drawings | Shop drawings including elevations, door details, frame details, reinforcement and hardware preparations, wall opening conditions, electrical raceway preparation, anchorages, joints, field splices, connections, accessories, moldings, removable stops, and glazing |  |  | draft |  |  |  |  | 0
CL-0001-115 | 08 36 12 | INSULATED SECTIONAL OVERHEAD STEEL DOORS | certificates | Qualification data for Installer. |  |  | draft |  |  |  |  | 0
CL-0001-116 | 08 36 12 | INSULATED SECTIONAL OVERHEAD STEEL DOORS | closeout | Finish warranty. |  |  | draft |  |  |  |  | 0
CL-0001-117 | 08 36 12 | INSULATED SECTIONAL OVERHEAD STEEL DOORS | closeout | Manufacturer's warranty. |  |  | draft |  |  |  |  | 0
CL-0001-118 | 08 36 12 | INSULATED SECTIONAL OVERHEAD STEEL DOORS | manuals | Maintenance data for sectional doors to include in maintenance manuals, including replacement parts list. |  |  | draft |  |  |  |  | 0
CL-0001-119 | 08 36 12 | INSULATED SECTIONAL OVERHEAD STEEL DOORS | product_data | Product data for each type and size of sectional door and accessory, including manufacturer’s installation instructions, construction details, material descriptions, dimensions of individual components, profile door sections, finishes, and, for power-operated doors, rated capacities, operating characteristics, electrical characteristics, and furnished accessories. |  |  | draft |  |  |  |  | 0
CL-0001-120 | 08 36 12 | INSULATED SECTIONAL OVERHEAD STEEL DOORS | samples | Samples for each exposed product and for each color and texture specified, in manufacturer's standard size. |  |  | draft |  |  |  |  | 0
CL-0001-121 | 08 36 12 | INSULATED SECTIONAL OVERHEAD STEEL DOORS | shop_drawings | Shop drawings for each installation and for components not dimensioned or detailed in manufacturer's product data, including plans, elevations, sections, mounting details, details of equipment assemblies, dimensions, required clearances, method of field assembly, components, location and size of each field connection, points of attachment with corresponding static and dynamic loads imposed on structure, and diagrams for power, signal, and control wiring. |  |  | draft |  |  |  |  | 0
CL-0001-122 | 08 51 13 | ALUMINUM WINDOWS | certificates | Qualification data for manufacturer and Installer, including names and address of 3 similar projects that Installer has worked on during the past 5 years. |  |  | draft |  |  |  |  | 0
CL-0001-123 | 08 51 13 | ALUMINUM WINDOWS | closeout | Sample warranties for manufacturer's warranties. |  |  | draft |  |  |  |  | 0
CL-0001-124 | 08 51 13 | ALUMINUM WINDOWS | other | Field quality-control reports. |  |  | draft |  |  |  |  | 0
CL-0001-125 | 08 51 13 | ALUMINUM WINDOWS | product_data | Product data for each type of aluminum window, including construction details, material descriptions, glazing and fabrication methods, dimensions of individual components and profiles, hardware, and finishes; include manufacturer’s installation instructions. |  |  | draft |  |  |  |  | 0
CL-0001-126 | 08 51 13 | ALUMINUM WINDOWS | samples | One full size unit, including insect screen and hardware; provide manufacturer’s standard color finishes for selection. |  |  | draft |  |  |  |  | 0
CL-0001-127 | 08 51 13 | ALUMINUM WINDOWS | samples | Sample corner section for each type of window unit and for each color specified, 8 by 8 inches in size; include frame, sash, and insect screen; provide manufacturer’s standard color finishes for selection. |  |  | draft |  |  |  |  | 0
CL-0001-128 | 08 51 13 | ALUMINUM WINDOWS | schedule | Product schedule for aluminum windows using same designations indicated on Drawings. |  |  | draft |  |  |  |  | 0
CL-0001-129 | 08 51 13 | ALUMINUM WINDOWS | shop_drawings | Shop drawings for aluminum windows, including plans, elevations, sections, hardware, accessories, insect screens, operational clearances, and details of installation including anchor, flashing, and sealant installation. |  |  | draft |  |  |  |  | 0
CL-0001-130 | 08 51 13 | ALUMINUM WINDOWS | test_reports | Product test reports for each type of aluminum window, for tests performed by a qualified testing agency. |  |  | draft |  |  |  |  | 0
CL-0001-131 | 08 71 00 | DOOR HARDWARE | certificates | Product certificates for each type of electrified door hardware, certifying compliance of fire-rated door hardware with listed fire-rated door assemblies |  |  | draft |  |  |  |  | 0
CL-0001-132 | 08 71 00 | DOOR HARDWARE | closeout | Maintenance data for each type of door hardware to include in maintenance manuals |  |  | draft |  |  |  |  | 0
CL-0001-133 | 08 71 00 | DOOR HARDWARE | other | Field quality-control reports |  |  | draft |  |  |  |  | 0
CL-0001-134 | 08 71 00 | DOOR HARDWARE | other | Qualification data for Installer |  |  | draft |  |  |  |  | 0
CL-0001-135 | 08 71 00 | DOOR HARDWARE | other | Sample warranty for special warranty |  |  | draft |  |  |  |  | 0
CL-0001-136 | 08 71 00 | DOOR HARDWARE | product_data | Manufacturer’s installation instructions provided along with product data |  |  | draft |  |  |  |  | 0
CL-0001-137 | 08 71 00 | DOOR HARDWARE | product_data | Product data for each type of product, including construction details, material descriptions, dimensions of individual components and profiles, and finishes |  |  | draft |  |  |  |  | 0
CL-0001-138 | 08 71 00 | DOOR HARDWARE | samples | Samples for each exposed product in each finish specified, in manufacturer's standard size |  |  | draft |  |  |  |  | 0
CL-0001-139 | 08 71 00 | DOOR HARDWARE | samples | Samples for initial selection for each type of exposed finish |  |  | draft |  |  |  |  | 0
CL-0001-140 | 08 71 00 | DOOR HARDWARE | samples | Samples for verification for each type of exposed product, in each finish specified |  |  | draft |  |  |  |  | 0
CL-0001-141 | 08 71 00 | DOOR HARDWARE | schedule | Door hardware schedule prepared by or under the supervision of Installer's Architectural Hardware Consultant |  |  | draft |  |  |  |  | 0
CL-0001-142 | 08 71 00 | DOOR HARDWARE | schedule | Final door hardware and keying schedule |  |  | draft |  |  |  |  | 0
CL-0001-143 | 08 71 00 | DOOR HARDWARE | schedule | Keying schedule prepared by or under the supervision of Installer's Architectural Hardware Consultant, detailing Director’s Representative’s final keying instructions for locks, including schematic keying diagram and index of key sets to unique door designations |  |  | draft |  |  |  |  | 0
CL-0001-144 | 08 71 00 | DOOR HARDWARE | shop_drawings | Shop drawings for electrified door hardware, including diagrams for power, signal, and control wiring and details of interface with building safety and security systems |  |  | draft |  |  |  |  | 0
CL-0001-145 | 08 71 00 | DOOR HARDWARE | test_reports | Product test reports for compliance with accessibility requirements, for tests performed by manufacturer and witnessed by a qualified testing agency, for door hardware on doors located in accessible routes |  |  | draft |  |  |  |  | 0
CL-0001-146 | 08 91 19 | FIXED LOUVERS | closeout | Sample warranties for manufacturer's special warranties. |  |  | draft |  |  |  |  | 0
CL-0001-147 | 08 91 19 | FIXED LOUVERS | design_data | Delegated design submittal for louvers indicated to comply with structural and seismic performance requirements and design criteria, including signed and sealed analysis data prepared by the qualified professional engineer. |  |  | draft |  |  |  |  | 0
CL-0001-148 | 08 91 19 | FIXED LOUVERS | product_data | Product data for each type of product, including printed catalog pages showing specified AMCA-certified models and manufacturer’s installation instructions. |  |  | draft |  |  |  |  | 0
CL-0001-149 | 08 91 19 | FIXED LOUVERS | samples | Samples for each type of metal finish required. |  |  | draft |  |  |  |  | 0
CL-0001-150 | 08 91 19 | FIXED LOUVERS | shop_drawings | Shop drawings for louvers and accessories, including plans, elevations, sections, details, attachments to other work, frame profiles, blade profiles, angles, spacing, weep paths, gaskets, flashings, sealants, and mullion profiles and locations. |  |  | draft |  |  |  |  | 0
CL-0001-151 | 08 91 19 | FIXED LOUVERS | test_reports | Product test reports for each type of louver, based on comprehensive tests performed in accordance with AMCA 500-L and showing compliance with specified performance requirements. |  |  | draft |  |  |  |  | 0
CL-0001-152 | 08 91 19 | FIXED LOUVERS | test_reports | Windborne-debris-impact-resistance test reports. |  |  | draft |  |  |  |  | 0
CL-0001-153 | 09 22 16 | NON-STRUCTURAL METAL FRAMING | certificates | Product certificates for each type of code-compliance certification for studs and tracks |  |  | draft |  |  |  |  | 0
CL-0001-154 | 09 22 16 | NON-STRUCTURAL METAL FRAMING | product_data | Product Data for each type of product |  |  | draft |  |  |  |  | 0
CL-0001-155 | 09 22 16 | NON-STRUCTURAL METAL FRAMING | samples | Samples of steel framing, fasteners, and clips/accessories |  |  | draft |  |  |  |  | 0
CL-0001-156 | 09 22 16 | NON-STRUCTURAL METAL FRAMING | test_reports | Evaluation reports for embossed, high-strength steel studs and tracks and post-installed anchors |  |  | draft |  |  |  |  | 0
CL-0001-157 | 09 29 00 | GYPSUM BOARD | product_data | Catalog sheets, specifications and installation instructions for Gypsum wallboard, Gypsum board, Type X, Water-resistant gypsum backing board, Interior trim, Sound-attenuation blankets, and Acoustical sealant |  |  | draft |  |  |  |  | 0
CL-0001-158 | 09 29 00 | GYPSUM BOARD | samples | Samples for initial selection of trim accessories |  |  | draft |  |  |  |  | 0
CL-0001-159 | 09 29 00 | GYPSUM BOARD | samples | Samples for trim accessories and fasteners |  |  | draft |  |  |  |  | 0
CL-0001-160 | 09 29 00 | GYPSUM BOARD | samples | Samples for verification of trim accessories |  |  | draft |  |  |  |  | 0
CL-0001-161 | 09 30 13 | CERAMIC TILING | certificates | Master Grade Certificates for each shipment, type, and composition of tile, signed by tile manufacturer and Installer |  |  | draft |  |  |  |  | 0
CL-0001-162 | 09 30 13 | CERAMIC TILING | certificates | Product Certificates for each type of product |  |  | draft |  |  |  |  | 0
CL-0001-163 | 09 30 13 | CERAMIC TILING | other | Qualification data for installer, including names, certificates, addresses, and project references |  |  | draft |  |  |  |  | 0
CL-0001-164 | 09 30 13 | CERAMIC TILING | product_data | Product Data for each type of product | Custom Building Products, Laticrete International, Inc., MAPEI Corporation, Summitville Tiles, Inc. | Improved Modified Dry-Set Mortar (Thinset), High-Performance Tile Grout, Improved Modified Dry-Set Mortar (Thinset), High-Performance Tile Grout | draft |  |  |  |  | 0
CL-0001-165 | 09 30 13 | CERAMIC TILING | samples | Full-size units of each type and composition of tile and for each color and finish required | Crossville, American Marazzi Tile, Inc., American Olean; a division of Dal-Tile Corporation., Daltile | Porcelain Floor tile, Porcelain Floor tile, Porcelain Floor tile, Porcelain Floor tile | draft |  |  |  |  | 0
CL-0001-166 | 09 30 13 | CERAMIC TILING | samples | Full-size units of each type of trim and accessory for each color and finish required | Blanke Corporation, Dural, Schluter Systems L.P. | Metal Edge Strips, Metal Edge Strips, Metal Edge Strips | draft |  |  |  |  | 0
CL-0001-167 | 09 30 13 | CERAMIC TILING | samples | Metal edge strips in 6-inch lengths | Blanke Corporation, Dural, Schluter Systems L.P. | Metal Edge Strips, Metal Edge Strips, Metal Edge Strips | draft |  |  |  |  | 0
CL-0001-168 | 09 30 13 | CERAMIC TILING | samples | Samples for initial selection for tile, grout, and accessories involving color selection |  |  | draft |  |  |  |  | 0
CL-0001-169 | 09 30 13 | CERAMIC TILING | samples | Samples for verification |  |  | draft |  |  |  |  | 0
CL-0001-170 | 09 30 13 | CERAMIC TILING | shop_drawings | Shop Drawings showing locations of each type of tile and tile pattern, and widths, details, and locations of expansion, contraction, control, and isolation joints in tile substrates and finished tile surfaces |  |  | draft |  |  |  |  | 0
CL-0001-171 | 09 30 13 | CERAMIC TILING | test_reports | Product Test Reports for tile-setting and -grouting products and certified porcelain tile | Custom Building Products, Laticrete International, Inc., MAPEI Corporation, Summitville Tiles, Inc. | Improved Modified Dry-Set Mortar (Thinset), High-Performance Tile Grout, Improved Modified Dry-Set Mortar (Thinset), High-Performance Tile Grout | draft |  |  |  |  | 0
CL-0001-172 | 09 51 23 | ACOUSTICAL TILE CEILINGS | certificates | Qualification Data for testing agency |  |  | draft |  |  |  |  | 0
CL-0001-173 | 09 51 23 | ACOUSTICAL TILE CEILINGS | certificates | Quality Control Submittals: Installer’s Qualifications Data and Company Field Advisor Data |  |  | draft |  |  |  |  | 0
CL-0001-174 | 09 51 23 | ACOUSTICAL TILE CEILINGS | closeout | Maintenance Data for finishes to include in maintenance manuals |  |  | draft |  |  |  |  | 0
CL-0001-175 | 09 51 23 | ACOUSTICAL TILE CEILINGS | design_data | Delegated-Design Submittal for seismic restraints for ceiling systems, including design calculations and analysis data signed and sealed by the qualified professional engineer |  |  | draft |  |  |  |  | 0
CL-0001-176 | 09 51 23 | ACOUSTICAL TILE CEILINGS | other | Evaluation Reports for each acoustical tile ceiling suspension system and anchor and fastener type, from ICC-ES |  |  | draft |  |  |  |  | 0
CL-0001-177 | 09 51 23 | ACOUSTICAL TILE CEILINGS | other | Field quality-control reports |  |  | draft |  |  |  |  | 0
CL-0001-178 | 09 51 23 | ACOUSTICAL TILE CEILINGS | product_data | Manufacturer’s installation instructions, along with product data | Armstrong World Industries, Inc., CertainTeed Corporation, Saint-Gobain North America, USG Corporation | Acoustical Tiles | draft |  |  |  |  | 0
CL-0001-179 | 09 51 23 | ACOUSTICAL TILE CEILINGS | product_data | Product data for each type of product including product testing data |  |  | draft |  |  |  |  | 0
CL-0001-180 | 09 51 23 | ACOUSTICAL TILE CEILINGS | samples | Samples for Initial Selection for components with factory-applied finishes |  |  | draft |  |  |  |  | 0
CL-0001-181 | 09 51 23 | ACOUSTICAL TILE CEILINGS | samples | Samples for Verification for each component indicated and for each exposed finish required |  |  | draft |  |  |  |  | 0
CL-0001-182 | 09 51 23 | ACOUSTICAL TILE CEILINGS | samples | Samples for each exposed product and for each color and texture specified, 6 inches in size |  |  | draft |  |  |  |  | 0
CL-0001-183 | 09 51 23 | ACOUSTICAL TILE CEILINGS | shop_drawings | Coordination Drawings: Reflected ceiling plans, drawn to scale, coordinating ceiling suspension-system members, structural members, hanger attachment methods, access modules, and ceiling penetrations |  |  | draft |  |  |  |  | 0
CL-0001-184 | 09 51 23 | ACOUSTICAL TILE CEILINGS | test_reports | Product Test Reports for each acoustical tile ceiling, for tests performed by a qualified testing agency |  |  | draft |  |  |  |  | 0
CL-0001-185 | 09 65 13 | RESILIENT BASE AND ACCESSORIES | product_data | Product Data for each type of product | Armstrong World Industries, Inc., Johnsonite; a Tarkett company., Roppe Corporation; Roppe Holding Company., VPI Corporation. | Thermoplastic-rubber base | draft |  |  |  |  | 0
CL-0001-186 | 09 65 13 | RESILIENT BASE AND ACCESSORIES | samples | Samples for Initial Selection for each type of product indicated |  |  | draft |  |  |  |  | 0
CL-0001-187 | 09 65 13 | RESILIENT BASE AND ACCESSORIES | samples | Samples for Verification for each type of product indicated and for each color, texture, and pattern required in manufacturer's standard-size Samples, but not less than 12 inches long |  |  | draft |  |  |  |  | 0
CL-0001-188 | 09 65 13 | RESILIENT BASE AND ACCESSORIES | samples | Samples for each exposed product and for each color and texture specified, not less than 12 inches long |  |  | draft |  |  |  |  | 0
CL-0001-189 | 09 65 13 | RESILIENT BASE AND ACCESSORIES | schedule | Product Schedule for resilient base and accessory products; use same designations indicated on Drawings |  |  | draft |  |  |  |  | 0
CL-0001-190 | 09 65 43 | LINOLEUM FLOORING | closeout | Maintenance data for each type of linoleum flooring to include in maintenance manuals |  |  | draft |  |  |  |  | 0
CL-0001-191 | 09 65 43 | LINOLEUM FLOORING | other | Qualification data for Installer |  |  | draft |  |  |  |  | 0
CL-0001-192 | 09 65 43 | LINOLEUM FLOORING | product_data | Product data for each type of product, including manufacturer's installation instructions |  |  | draft |  |  |  |  | 0
CL-0001-193 | 09 65 43 | LINOLEUM FLOORING | samples | Heat-welded seam samples for each linoleum flooring product and welding bead color and pattern combination required, with seam running lengthwise and in center of 6-by-9-inch sample applied to rigid backing and prepared by Installer for this Project |  |  | draft |  |  |  |  | 0
CL-0001-194 | 09 65 43 | LINOLEUM FLOORING | samples | Samples for each exposed product and each color and pattern specified, in manufacturer's standard size, not less than 6-by-9-inch sections; include heat-welding bead samples, not less than 9 inches long, of each color required |  |  | draft |  |  |  |  | 0
CL-0001-195 | 09 65 43 | LINOLEUM FLOORING | samples | Samples for initial selection for each type of linoleum flooring indicated |  |  | draft |  |  |  |  | 0
CL-0001-196 | 09 65 43 | LINOLEUM FLOORING | samples | Samples for verification for each type of linoleum flooring, in manufacturer's standard size, not less than 6-by-9-inch sections of each different color and pattern required |  |  | draft |  |  |  |  | 0
CL-0001-197 | 09 65 43 | LINOLEUM FLOORING | schedule | Product schedule for linoleum flooring, using same designations indicated on Drawings |  |  | draft |  |  |  |  | 0
CL-0001-198 | 09 65 43 | LINOLEUM FLOORING | shop_drawings | Shop drawings for each type of linoleum flooring, including flooring layouts, locations of seams, edges, columns, doorways, enclosing partitions, built-in furniture, cabinets, cutouts, and special patterns |  |  | draft |  |  |  |  | 0
CL-0001-199 | 09 91 23 | INTERIOR PAINTING | certificates | Certification of Volatile Organic Compounds; certified list demonstrating compliance requirements in Quality Assurance Article. |  |  | draft |  |  |  |  | 0
CL-0001-200 | 09 91 23 | INTERIOR PAINTING | other | Contractor’s Qualifications documentation demonstrating compliance with requirements in Quality Assurance Article. |  |  | draft |  |  |  |  | 0
CL-0001-201 | 09 91 23 | INTERIOR PAINTING | product_data | Product Data for each type of product, including preparation requirements, application instructions, current MPI Approved Products List printout for each specified product category with the proposed product highlighted, VOC content, and manufacturer’s standard colors in the form of actual fan decks. |  |  | draft |  |  |  |  | 0
CL-0001-202 | 09 91 23 | INTERIOR PAINTING | samples | Samples for Initial Selection for each type of topcoat product. |  |  | draft |  |  |  |  | 0
CL-0001-203 | 09 91 23 | INTERIOR PAINTING | samples | Samples for Verification for each type of paint system and in each color and gloss of topcoat; submit on rigid backing, 8 inches square, with coats applied in steps and each coat and sample labeled. |  |  | draft |  |  |  |  | 0
CL-0001-204 | 09 91 23 | INTERIOR PAINTING | schedule | Painting Schedule: Cross-referenced Painting Schedule listing all interior substrates to be painted and specified finish paint type designation; product name and manufacturer, recommended primers and product numbers, and finish paint color designation for each substrate to be painted. |  |  | draft |  |  |  |  | 0
CL-0001-205 | 10 28 00 | TOILET, BATH, AND LAUNDRY ACCESSORIES | design_data | Delegated-design submittal for grab bars, including structural design calculations indicating compliance with specified structural-performance requirements |  |  | draft |  |  |  |  | 0
CL-0001-206 | 10 28 00 | TOILET, BATH, AND LAUNDRY ACCESSORIES | other | Maintenance Data for accessories to include in maintenance manuals |  |  | draft |  |  |  |  | 0
CL-0001-207 | 10 28 00 | TOILET, BATH, AND LAUNDRY ACCESSORIES | product_data | Product Data for each type of product, including construction details, material descriptions, dimensions of individual components and profiles, finishes, anchoring and mounting requirements, cutouts in other work and substrate preparation, and electrical characteristics |  |  | draft |  |  |  |  | 0
CL-0001-208 | 10 28 00 | TOILET, BATH, AND LAUNDRY ACCESSORIES | samples | Samples for each exposed product and for each finish specified, full size |  |  | draft |  |  |  |  | 0
CL-0001-209 | 10 28 00 | TOILET, BATH, AND LAUNDRY ACCESSORIES | schedule | Product Schedule indicating types, quantities, sizes, and installation locations by room of each accessory required |  |  | draft |  |  |  |  | 0
CL-0001-210 | 12 36 61 | SOLID SURFACING COUNTERTOPS | closeout | Maintenance data for solid surface material countertops, including product data for care products used or recommended by Installer and names, addresses, and telephone numbers of local sources for products |  |  | draft |  |  |  |  | 0
CL-0001-211 | 12 36 61 | SOLID SURFACING COUNTERTOPS | product_data | Product data for countertop materials, including manufacturer’s installation instructions |  |  | draft |  |  |  |  | 0
CL-0001-212 | 12 36 61 | SOLID SURFACING COUNTERTOPS | samples | Samples for initial selection for each type of material exposed to view |  |  | draft |  |  |  |  | 0
CL-0001-213 | 12 36 61 | SOLID SURFACING COUNTERTOPS | samples | Samples for verification for countertop material, including one full-size solid surface material countertop with front edge and backsplash |  |  | draft |  |  |  |  | 0
CL-0001-214 | 12 36 61 | SOLID SURFACING COUNTERTOPS | shop_drawings | Shop drawings for countertops showing materials, finishes, edge and backsplash profiles, methods of joining, cutouts for plumbing fixtures, locations and details of joints, and direction of directional pattern, if any |  |  | draft |  |  |  |  | 0
CL-0001-215 | 13 34 19 | METAL BUILDING SYSTEMS | certificates | Erector Certificates for qualified erector, from manufacturer. |  |  | draft |  |  |  |  | 0
CL-0001-216 | 13 34 19 | METAL BUILDING SYSTEMS | certificates | Letter of Design Certification signed and sealed by a qualified Professional Engineer, including project, order, manufacturer, contractor, building dimensions, code compliance, design loads, load combinations, and building-use category. |  |  | draft |  |  |  |  | 0
CL-0001-217 | 13 34 19 | METAL BUILDING SYSTEMS | certificates | Welding certificates. |  |  | draft |  |  |  |  | 0
CL-0001-218 | 13 34 19 | METAL BUILDING SYSTEMS | closeout | Maintenance Data for metal panel finishes and door hardware to include in maintenance manuals. |  |  | draft |  |  |  |  | 0
CL-0001-219 | 13 34 19 | METAL BUILDING SYSTEMS | design_data | Delegated-Design Submittal for metal building systems; include analysis data indicating compliance with performance requirements and design data signed and sealed by the qualified professional engineer. |  |  | draft |  |  |  |  | 0
CL-0001-220 | 13 34 19 | METAL BUILDING SYSTEMS | other | Field quality-control reports. |  |  | draft |  |  |  |  | 0
CL-0001-221 | 13 34 19 | METAL BUILDING SYSTEMS | other | Sample Warranties for special warranties. |  |  | draft |  |  |  |  | 0
CL-0001-222 | 13 34 19 | METAL BUILDING SYSTEMS | other | Source quality-control reports. |  |  | draft |  |  |  |  | 0
CL-0001-223 | 13 34 19 | METAL BUILDING SYSTEMS | other | Surveys showing final elevations and locations of major members, with discrepancies between actual installation and Contract Documents identified and surveyor certification of accuracy. |  |  | draft |  |  |  |  | 0
CL-0001-224 | 13 34 19 | METAL BUILDING SYSTEMS | product_data | Product Data for each type of metal building system component; include construction details, material descriptions, dimensions of individual components and profiles, and finishes for insulated metal roof panels and insulated metal wall panels. |  |  | draft |  |  |  |  | 0
CL-0001-225 | 13 34 19 | METAL BUILDING SYSTEMS | samples | Samples for initial selection for units with factory-applied finishes. |  |  | draft |  |  |  |  | 0
CL-0001-226 | 13 34 19 | METAL BUILDING SYSTEMS | samples | Samples for verification for panels, flashing and trim, vapor-retarder facings, windows, and accessories, including exposed accessories where specified. |  |  | draft |  |  |  |  | 0
CL-0001-227 | 13 34 19 | METAL BUILDING SYSTEMS | schedule | Door Schedule for doors and frames; include details of reinforcement. Include Door Hardware Schedule and Keying Schedule. |  |  | draft |  |  |  |  | 0
CL-0001-228 | 13 34 19 | METAL BUILDING SYSTEMS | shop_drawings | Shop Drawings including full building plan, elevations, sections, details, and anchor-rod plans/templates; structural-framing drawings; metal roof and wall panel layout drawings; and accessory drawings for flashing and trim, gutters, and downspouts. |  |  | draft |  |  |  |  | 0
CL-0001-229 | 13 34 19 | METAL BUILDING SYSTEMS | test_reports | Material Test Reports for structural steel, bolts/nuts/washers, tension-control high-strength bolt-nut-washer assemblies, shop primers, and nonshrink grout. |  |  | draft |  |  |  |  | 0
CL-0001-230 | 31 00 00 | EARTHWORK | other | Qualification data for qualified testing agency |  |  | draft |  |  |  |  | 0
CL-0001-231 | 31 00 01 | EARTHWORK MATERIALS | certificates | Qualification data for ASTM certified soils testing agency |  |  | draft |  |  |  |  | 0
CL-0001-232 | 31 00 01 | EARTHWORK MATERIALS | certificates | Supplier’s certificate certifying products meet or exceed specified requirements |  |  | draft |  |  |  |  | 0
CL-0001-233 | 31 00 01 | EARTHWORK MATERIALS | product_data | Name of imported materials source |  |  | draft |  |  |  |  | 0
CL-0001-234 | 31 00 01 | EARTHWORK MATERIALS | samples | Samples of select granular material, subbase course type 2, selected fill, cushion material, Item B-12, and crushed stone; include laboratory test results for gradation, Proctors and soundness tests |  |  | draft |  |  |  |  | 0
CL-0001-235 | 31 00 01 | EARTHWORK MATERIALS | test_reports | Material test reports for each on-site and borrow soil material proposed for fill and backfill, including ASTM D2487 classification and ASTM D1557 laboratory compaction curve |  |  | draft |  |  |  |  | 0
CL-0001-236 | 31 25 00 | EROSION AND SEDIMENTATION CONTROLS | certificates | Manufacturer's certificate certifying products meet or exceed specified requirements |  |  | draft |  |  |  |  | 0
CL-0001-237 | 31 25 00 | EROSION AND SEDIMENTATION CONTROLS | design_data | Proposed mix design of each class of concrete |  |  | draft |  |  |  |  | 0
CL-0001-238 | 31 25 00 | EROSION AND SEDIMENTATION CONTROLS | product_data | Data on temporary and permanent erosion and sediment control measures |  |  | draft |  |  |  |  | 0
CL-0001-239 | 31 25 00 | EROSION AND SEDIMENTATION CONTROLS | samples | Two samples of rock, minimum 5 tons each or one-half total Project quantity, whichever is smaller |  |  | draft |  |  |  |  | 0
CL-0001-240 | 31 25 00 | EROSION AND SEDIMENTATION CONTROLS | test_reports | Certified test results for precast concrete at manufacturing facility, cast-in-place concrete in field, and granular backfill |  |  | draft |  |  |  |  | 0
CL-0001-241 | 31 50 00 | EXCAVATION SUPPORT AND PROTECTION | closeout | Record drawings identifying locations and depths of capped utilities, abandoned-in-place support and protection systems, and other subsurface structural, electrical, or mechanical conditions |  |  | draft |  |  |  |  | 0
CL-0001-242 | 31 50 00 | EXCAVATION SUPPORT AND PROTECTION | design_data | Contractor calculations for excavation support and protection system, including analysis data signed and sealed by the New York State licensed Professional Engineer responsible for preparation |  |  | draft |  |  |  |  | 0
CL-0001-243 | 31 50 00 | EXCAVATION SUPPORT AND PROTECTION | design_data | Delegated-design submittal for excavation support and protection systems, including analysis data signed and sealed by the New York State licensed Professional Engineer responsible for preparation |  |  | draft |  |  |  |  | 0
CL-0001-244 | 31 50 00 | EXCAVATION SUPPORT AND PROTECTION | other | Qualification data for Land Surveyor and Professional Engineer |  |  | draft |  |  |  |  | 0
CL-0001-245 | 31 50 00 | EXCAVATION SUPPORT AND PROTECTION | product_data | Product data for each type of product, including construction details, material and accessory descriptions, performance properties, dimensions of individual components and profiles, and calculations for excavation support and protection system |  |  | draft |  |  |  |  | 0
CL-0001-246 | 31 50 00 | EXCAVATION SUPPORT AND PROTECTION | shop_drawings | Shop drawings for excavation support and protection system, including plans, elevations, sections, details, arrangement and locations of soldier piles, piling, lagging, tiebacks, bracing, other components, type and location of waterproofing, and written excavation support and protection plan with intended excavation procedure, sequence of construction, and tolerances |  |  | draft |  |  |  |  | 0
CL-0001-247 | 32 12 16 | ASPHALT PAVING | certificates | Certification, by authorities having jurisdiction, of approval of each asphalt design proposed for the Work. |  |  | draft |  |  |  |  | 0
CL-0001-248 | 32 12 16 | ASPHALT PAVING | other | Field quality-control reports. |  |  | draft |  |  |  |  | 0
CL-0001-249 | 32 12 16 | ASPHALT PAVING | product_data | Joint sealant product data, including manufacturer/provider/plant name, product name, technical data, and tested physical and performance properties. |  |  | draft |  |  |  |  | 0
CL-0001-250 | 32 12 16 | ASPHALT PAVING | product_data | NYSDOT Approved Plant name, number, and location of the asphalt plant for each asphalt design proposed for the Work. |  |  | draft |  |  |  |  | 0
CL-0001-251 | 32 12 16 | ASPHALT PAVING | product_data | Qualification data for paving-mix manufacturer and testing agency. |  |  | draft |  |  |  |  | 0
CL-0001-252 | 32 12 16 | ASPHALT PAVING | test_reports | Asphalt mix design test results less than 6 months old for each mix proposed for the Work. |  |  | draft |  |  |  |  | 0
CL-0001-253 | 32 17 23 | PAVEMENT MARKINGS | certificates | Affidavit by the paint applicator certifying that the materials comply with the current regulatory requirements in effect at the time products were delivered and applied |  |  | draft |  |  |  |  | 0
CL-0001-254 | 32 17 23 | PAVEMENT MARKINGS | product_data | Manufacturer’s installation instructions and product data |  |  | draft |  |  |  |  | 0
CL-0001-255 | 32 17 23 | PAVEMENT MARKINGS | product_data | Product data including technical data and tested physical and performance properties |  |  | draft |  |  |  |  | 0
CL-0001-256 | 32 17 23 | PAVEMENT MARKINGS | samples | Samples for each exposed product and for each color and texture specified; on rigid backing, 8 inches square |  |  | draft |  |  |  |  | 0
CL-0001-257 | 33 01 10 | DISINFECTION OF WATER UTILITY PIPING SYSTEMS | certificates | Certification that final water complies with disinfectant quality standards of the New York State Department of Health |  |  | draft |  |  |  |  | 0
CL-0001-258 | 33 01 10 | DISINFECTION OF WATER UTILITY PIPING SYSTEMS | certificates | Manufacturer's certificate certifying products meet or exceed specified requirements |  |  | draft |  |  |  |  | 0
CL-0001-259 | 33 01 10 | DISINFECTION OF WATER UTILITY PIPING SYSTEMS | closeout | Disinfection report including type and form of disinfectant used, date and time of disinfectant injection start and completion, test locations, name of person collecting samples, initial and 24-hour disinfectant residuals in treated water in ppm for each outlet tested, date and time of flushing start and completion, and disinfectant residual after flushing in ppm for each outlet tested |  |  | draft |  |  |  |  | 0
CL-0001-260 | 33 01 10 | DISINFECTION OF WATER UTILITY PIPING SYSTEMS | other | Disinfection procedure, including type of disinfectant and calculations indicating quantities of disinfectants required to produce specified chlorine concentration |  |  | draft |  |  |  |  | 0
CL-0001-261 | 33 01 10 | DISINFECTION OF WATER UTILITY PIPING SYSTEMS | other | Field quality-control submittals indicating results of Contractor-furnished tests and inspections |  |  | draft |  |  |  |  | 0
CL-0001-262 | 33 01 10 | DISINFECTION OF WATER UTILITY PIPING SYSTEMS | other | Qualifications statements for manufacturer and applicator |  |  | draft |  |  |  |  | 0
CL-0001-263 | 33 01 10 | DISINFECTION OF WATER UTILITY PIPING SYSTEMS | product_data | Manufacturer information for proposed chemicals and treatment doses |  |  | draft |  |  |  |  | 0
CL-0001-264 | 33 01 10 | DISINFECTION OF WATER UTILITY PIPING SYSTEMS | product_data | Manufacturer’s installation instructions and product data |  |  | draft |  |  |  |  | 0
CL-0001-265 | 33 01 10 | DISINFECTION OF WATER UTILITY PIPING SYSTEMS | test_reports | Test and evaluation reports indicating testing results comparative to specified requirements |  |  | draft |  |  |  |  | 0
CL-0001-266 | 33 14 16 | SITE WATER UTILITY DISTRIBUTION PIPING | certificates | Manufacturer's certificate certifying products meet or exceed specified requirements |  |  | draft |  |  |  |  | 0
CL-0001-267 | 33 14 16 | SITE WATER UTILITY DISTRIBUTION PIPING | closeout | Project Record Documents: Record actual locations of piping mains, valves, connections, thrust restraints, and invert elevations |  |  | draft |  |  |  |  | 0
CL-0001-268 | 33 14 16 | SITE WATER UTILITY DISTRIBUTION PIPING | other | Qualifications for manufacturer and installer |  |  | draft |  |  |  |  | 0
CL-0001-269 | 33 14 16 | SITE WATER UTILITY DISTRIBUTION PIPING | product_data | Manufacturer information regarding pipe materials, pipe fittings, valves, and accessories | A.Y. McDonald Mfg. Co, Mueller Water Products, Romac Industries Inc., Smith-Blair | Corporation Stop Assemblies | draft |  |  |  |  | 0
CL-0001-270 | 33 14 16 | SITE WATER UTILITY DISTRIBUTION PIPING | test_reports | Field quality-control results of Contractor-furnished tests and inspections |  |  | draft |  |  |  |  | 0
CL-0001-271 | 33 31 00 | SANITARY SEWERAGE PIPING | certificates | Manufacturer's certificate certifying products meet or exceed specified requirements |  |  | draft |  |  |  |  | 0
CL-0001-272 | 33 31 00 | SANITARY SEWERAGE PIPING | closeout | Project Record Documents recording finished locations of pipe runs, connections, manholes, cleanouts, and invert elevations |  |  | draft |  |  |  |  | 0
CL-0001-273 | 33 31 00 | SANITARY SEWERAGE PIPING | other | Qualifications statement for manufacturer and installer |  |  | draft |  |  |  |  | 0
CL-0001-274 | 33 31 00 | SANITARY SEWERAGE PIPING | product_data | Manufacturer information indicating pipe material to be used, pipe accessories | Fernco Inc., Romac Industries, Inc., A-Lok, Press-Seal Corporation | Flexible Couplings, Flexible Couplings, Flexible Pipe Boots for Manhole Pipe Entrances, Flexible Pipe Boots for Manhole Pipe Entrances | draft |  |  |  |  | 0
CL-0001-275 | 33 31 00 | SANITARY SEWERAGE PIPING | test_reports | Field quality-control submittals indicating results of Contractor-furnished tests and inspections |  |  | draft |  |  |  |  | 0
CL-0001-276 | 33 31 00 | SANITARY SEWERAGE PIPING | test_reports | Source quality-control submittals indicating results of shop tests and inspections |  |  | draft |  |  |  |  | 0
CL-0001-277 | 33 31 23 | SANITARY SEWERAGE FORCE MAIN PIPING | certificates | Manufacturer's certificate certifying products meet or exceed specified requirements |  |  | draft |  |  |  |  | 0
CL-0001-278 | 33 31 23 | SANITARY SEWERAGE FORCE MAIN PIPING | closeout | Project Record Documents: Record invert elevations and actual locations of pipe runs and connections |  |  | draft |  |  |  |  | 0
CL-0001-279 | 33 31 23 | SANITARY SEWERAGE FORCE MAIN PIPING | design_data | Shop drawings with design calculations and assumptions for restrained joints, including establishing lengths of restrained joint piping required; signed and sealed by a professional engineer licensed in the State of New York |  |  | draft |  |  |  |  | 0
CL-0001-280 | 33 31 23 | SANITARY SEWERAGE FORCE MAIN PIPING | other | Manufacturer instructions for special procedures required to install specified products |  |  | draft |  |  |  |  | 0
CL-0001-281 | 33 31 23 | SANITARY SEWERAGE FORCE MAIN PIPING | other | Qualifications for manufacturer, installer, and licensed professional |  |  | draft |  |  |  |  | 0
CL-0001-282 | 33 31 23 | SANITARY SEWERAGE FORCE MAIN PIPING | other | Results of contractor-furnished tests and inspections |  |  | draft |  |  |  |  | 0
CL-0001-283 | 33 31 23 | SANITARY SEWERAGE FORCE MAIN PIPING | product_data | Manufacturer information indicating pipe material used, pipe accessories, valves |  |  | draft |  |  |  |  | 0
CL-0001-284 | 33 31 23 | SANITARY SEWERAGE FORCE MAIN PIPING | shop_drawings | Piping piece numbers and locations; restrained joint locations |  |  | draft |  |  |  |  | 0
CL-0001-285 | 33 32 16 | PACKAGED WASTEWATER GRINDER PUMP ASSEMBLIES | certificates | Manufacturer's certificate certifying products meet or exceed specified requirements | Goulds Water Technology, Zoeller Company | Centrifugal Grinder Pumps | draft |  |  |  |  | 0
CL-0001-286 | 33 32 16 | PACKAGED WASTEWATER GRINDER PUMP ASSEMBLIES | closeout | Project Record Documents: Record actual locations and final orientation of equipment and accessories |  |  | draft |  |  |  |  | 0
CL-0001-287 | 33 32 16 | PACKAGED WASTEWATER GRINDER PUMP ASSEMBLIES | other | Detailed installation instructions, including storage and handling procedures, anchoring, and layout | Goulds Water Technology, Zoeller Company | Centrifugal Grinder Pumps | draft |  |  |  |  | 0
CL-0001-288 | 33 32 16 | PACKAGED WASTEWATER GRINDER PUMP ASSEMBLIES | other | Manufacturer reports certifying equipment has been installed according to manufacturer instructions | Goulds Water Technology, Zoeller Company | Centrifugal Grinder Pumps | draft |  |  |  |  | 0
CL-0001-289 | 33 32 16 | PACKAGED WASTEWATER GRINDER PUMP ASSEMBLIES | other | Qualifications for manufacturer and installer; manufacturer's approval of installer | Goulds Water Technology, Zoeller Company | Centrifugal Grinder Pumps | draft |  |  |  |  | 0
CL-0001-290 | 33 32 16 | PACKAGED WASTEWATER GRINDER PUMP ASSEMBLIES | other | Results of Contractor-furnished tests and inspections |  |  | draft |  |  |  |  | 0
CL-0001-291 | 33 32 16 | PACKAGED WASTEWATER GRINDER PUMP ASSEMBLIES | product_data | Manufacturer information concerning materials of construction and fabrication | Goulds Water Technology, Zoeller Company | Centrifugal Grinder Pumps | draft |  |  |  |  | 0
CL-0001-292 | 33 32 16 | PACKAGED WASTEWATER GRINDER PUMP ASSEMBLIES | shop_drawings | Detailed dimensions for materials and equipment, including pump basins, pumps, piping, controls including wiring schematics, and accessories | Goulds Water Technology, Zoeller Company | Centrifugal Grinder Pumps | draft |  |  |  |  | 0
CL-0001-293 | 33 42 00 | STORMWATER CONVEYANCE | other | Field quality-control reports |  |  | draft |  |  |  |  | 0
CL-0001-294 | 33 42 00 | STORMWATER CONVEYANCE | product_data | Manufacturer’s installation instructions, along with product data |  |  | draft |  |  |  |  | 0
CL-0001-295 | 33 42 00 | STORMWATER CONVEYANCE | product_data | Product data for each type of product | Neenah Foundry Company, East Jordan Iron Works, Josam Company | Cleanout Lids and Frames | draft |  |  |  |  | 0